## TestCase
Improvement
|  |  | field responsiveness | should instruct the user
|  |  | Session, Inactive | should forcefully logut |  | Project site | UpoharBd |  |  | TEST CASE
|  |  | limit consecutive login failures | should stop taking response |  | TC Start Date | 2022-09-15 | TC Execution Start Date | 2022-09-15 | PASS | 44
[6 empty] | TC End Date | 2022-09-25 | TC Execution End Date | 2022-09-20 | FAIL | 21
[6 empty] | Test Case Developed By | Sakif Abdullah | Browser (tested) | Yes | Not tested | 4
[6 empty] | Test Case Reviewed By |  | Performance (tested) | No | Out of Scope | 0
[10 empty] | TOTAL | 69
#SL | Module | Feature | Type of testing | Test Case | Expected Result | Actual Result | Test Data | Test Steps | Bug Screenshots | Status | Remarks
TC001 | User Management | Express Registration(Sign Up) | Accessibility testing | Verify whether Registration page appears | Registration required fields appears | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. |  | Passed
TC002 |  |  | Non functional testing | Common check of text fields | Correct labels are diplayed for the text field | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. |  | Passed
TC003 |  |  |  |  | Red * symbol for mandatory fields | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. |  | Passed
TC004 |  |  |  |  | prepopulated values should assignable | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on every field to check prepopulated vales |  | Passed
TC005 |  |  |  | Checking blank field reasult by clicking"submit & continue" | indicate to Assign required fields | executed" error red sign in every required field" |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Submit & continue" |  | Passed
TC006 |  |  |  |  | Warning message should be dispayled | executed"Incorrect or No Captcha Code Entered" |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Submit & continue" |  | Passed
TC007 |  |  |  | Checking empty field response | Should give a message to fillup every required field. | executed"Please make sure all required fields are completed." |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Submit & continue" |  | Passed
TC008 |  |  |  | Responsive field fill up cases | fillup immediate response like instruction for correctly execution | not executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Submit & continue" | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p1.PNG | Failed
TC009 |  |  |  | App onboarding Fragments | No spelling mistakes or gramatical errors | not executed"State/district/County" |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.Observe | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/g1.PNG | Failed
TC010 |  |  | Functional | Name fields(First Name, Last Name) with special charaters | should not take response or error indication | not executed"It take responses" | First Name: $@kif Last Name:@bdull?h | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p2.PNG | Failed
TC011 |  |  |  | Name fields with Number or only numbers | should not take response or error indication | not executed | 123 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p3.PNG | Failed
TC012 |  |  |  | Name fields with valid inputs | Should accept the input | executed | First Name: Sakif Last Name: Abdullah | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data |  | Passed
TC013 |  |  |  | Name fields response with space | should not take response or error indication | not executed | Sa kif | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p4.PNG | Failed
TC014 |  |  |  | Email field with empty input | should not take response or error indication | executed"Please make sure all required fields are completed." |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Submit & continue" |  | Passed
TC015 |  |  |  | Email field with invalid format | should not take response or error indication | executed"Please enter a valid email address." | sakif.gmai.com/ 1234/ abcd | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Email" Fields 4. enter test data |  | Passed
TC016 |  |  |  | Creating User with existing email account | Should not allow to make new account with existing email acount and should instruct by error indication | executed"Sorry but that email is assigned to an account holder." | sakif4646@gmail.com | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Email" Fields 4. enter test data |  | Passed
TC017 |  |  |  | Email field with non valid email | should not take response or error indication | not executed | sakif@gmail.com | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Email" Fields 4. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p5.PNG | Failed
TC018 |  |  |  | Phone No fields with speacial character | should not take response or error indication | executed "Telephone number must be Numeric" | $123& | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data |  | Passed
TC019 |  |  |  | Phone No fields with Alphabets | should not take response or error indication | executed "Telephone number must be Numeric" | abdil | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data |  | Passed
TC020 |  |  |  | Phone No fields with invalid country code match | should not take response or error indication | not executed | 7894382 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/phn6.PNG | Failed
TC021 |  |  |  | Phone No field with space | should not take response or error indication | not executed | 7894382 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/phn6.PNG | Failed
TC022 |  |  |  | Phone No field with more or less than 11 digits | should not take response or error indication | not executed | 7894 382 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/phn7.PNG | Failed
TC023 |  |  |  | Phone No fields with valid input | Should accept the input | executed | 01535421765 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data |  | Passed
TC024 |  |  |  | Password field with special characters | Should accept the input | executed | @la&90 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4.fill up with test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC025 |  |  |  | Password field with alphabets | Should accept the input | executed | abechg | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC026 |  |  |  | Password field with space inputs | Should accept the input | executed | ab 124 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC027 |  |  |  | Password field with numbers | Should accept the input | executed | 567829 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC028 |  |  |  | Password field with Uppercase and lower case characters | Should accept the input | executed | AaBcD | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC029 |  |  |  | Password field with mask | Should accept the input | executed | sak@006 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC030 |  |  |  | Password field with simple or common types(easy guessable) | should not accept response and should alert or instruct strong and combine input | not executed | 12345 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Failed
TC031 |  |  |  | Verify "Confirm Password" field case matching | should accept when accurate or exact password matched with "Choose Password" field | executed | Choose password: 3782 Confirm password: 3782 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC032 |  |  |  |  | should not accept and instruct to match with "Choose Password" field | executed"Please make sure your passwords match." | Choose password: 3782 Confirm password: 4672 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data |  | Passed
TC033 |  |  |  | Password field input length requirement(digits length) | should not accept without minimum inputs | not executed | abcd | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/pass1.PNG | Failed
TC034 |  |  |  | Address field with valid input | should accept the input | executed | Dhanmondi | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data |  | Passed
TC035 |  |  |  | Address field with unavailable or inappropriate inputs | Invalid message should be appear | not executed | wqw | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add1.PNG | Failed
TC036 |  |  |  | Verify Address field length | No limitation to filled this required filled | executed | Lalminir street | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data |  | Passed
TC037 |  |  |  | Address field only digits | Invalid message should be appear | not executed | 12124 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add2.PNG | Failed
TC038 |  |  |  | Address field with space input | should accept the response | executed | Lalminir street | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data |  | Passed
TC039 |  |  |  | Area/Town field with valid input | should accept the input | executed | 1ka | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data |  | Passed
TC040 |  |  |  | Area/Town field with unavailable or inappropriate inputs | Invalid message should be appear | not executed | 222 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add1.PNG | Failed
TC041 |  |  |  | Area/Town Address field length | No limitation to filled this required filled | executed | chowmohoni vatara | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data |  | Passed
TC042 |  |  |  | Area/Town field only digits | Invalid message should be appear | not executed | 222 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add2.PNG | Failed
TC043 |  |  |  | Area/Town field with space input | should accept the response | executed | chowmohoni vatara | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data |  | Passed
TC044 |  |  |  | Post/Zip code field only numeric | should be only numeric input | not executed | avafgufg | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Post/zip Code" Fields 4. fill test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/post1.PNG | Failed
TC045 |  |  |  | CLicking Country code dropdown button | Should show the list of country code available and select | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. Press desire one to check |  | Passed
TC046 |  |  |  | CLicking state/District/country dropdown button | should show the list of district/state/country available and select | not executed"Only executable for Bangladesh" | Delhi | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. Press Bangladesh 5. click on "state/District/country" feild to check dropdown list found 6. click on "Country code" Feild 7. click on any country expect Bangladesh 8. click on " state/District/country" feild which visible no dropdown list 9. fill with test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/country1.PNG | Failed
TC047 |  |  |  | State/District/country Field with invalid input | Invalid message should be appear | not executed | bdksdbka | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. click on any country expect Bangladesh 5. click on " state/District/country" feild which visible no dropdown list 6. fill with test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/country2.PNG | Failed
TC048 |  |  |  | State/District/country Field with only digits | Invalid message should be appear | not executed | 9898 | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. click on any country expect Bangladesh 5. click on " state/District/country" feild which visible no dropdown list 6. fill with test data | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/country3.PNG | Failed
TC049 |  |  |  | State/District/country Field length | No limitation to filled this required filled | executed | kolkata | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. click on any country expect Bangladesh 5. click on " state/District/country" feild which visible no dropdown list 6. fill with test data |  | Passed
TC050 |  |  |  | State/District/country Field with space input | should accept the response | executed | Mueang Samut Prakan | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. click on any country expect Bangladesh 5. click on " state/District/country" feild which visible no dropdown list 6. fill with test data |  | Passed
TC051 |  |  |  | Verifying reCAPCHA checkbox working | The checkbox should be checked | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.fill up all required fields 6. click beside"I'm not a robot" ior reCAPCHA button and follow its instruction |  | Passed
TC052 |  |  | Acceptance testing | Verifying Submit & continue works with proper action | should react on Event action | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3. fill up all required field with valid input 4. click on Submit & continue button |  | Passed
TC053 |  | My account(Log In) | Accessibility testing | Verifying whether Log In page appears | A Log UI should apear | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. |  | Passed
TC054 |  |  | Non functional testing | Grammatical or spelling mistake on Log In page | No grammatical or spelling mistake | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. |  | Passed
TC055 |  |  |  | Session, inactive , forcefully logout | Should forcefully logout or inactive in specific session/time | not executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. |  | Failed
TC056 |  |  |  | Responsiveness | fields with immediate response like instruction for correctly execution | not executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. |  | Failed
TC057 |  |  |  | limit consecutive login failures | Should stop taking response for limited period | unchecked |  |  |  | Not Executed
TC058 |  |  |  | Auto login for remember me button | should react on Event action | Unchecked |  |  |  | Not Executed
TC059 |  |  |  | checking Limit total no. of unsuccessful attempts | should stop taking response after few unsuccessful attempts | Unchecked |  |  |  | Not Executed
TC060 |  |  |  | Clicking Log In button keeping all field blank | Should appear an error message | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Log in" |  | Passed
TC061 |  |  | Functional testing | Valid email or phone and empty password | Should appear an error message | executed | sakif4646@gmail.com |  |  | Passed
TC062 |  |  |  | Invalid email and valid password | Should appear an error message | executed | sasa@gmail.com | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Password" field 4.fill with test data 5. click on" Log in" |  | Passed
TC063 |  |  |  | empty Email and valid password | Should appear an error message | executed | pass:565656 | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Password" field 4.fill with test data 5.click on "Log In" |  | Passed
TC064 |  |  |  | Checking password field is masked | Written password should be masked | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Password" field 4.fill with test data 5.Observe "******" appears |  | Passed
TC065 |  |  | Accessibility testing | Checking "Forgot password" hyperlink | should react on Event action | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Forgot Password" field |  | Passed
TC066 |  |  |  | Checking "Need to register" hyperlink | should react on Event action | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Need to register" field |  | Passed
TC067 |  |  |  | checking Limit total no. of unsuccessful attempts | should stop taking response after few unsuccessful attempts | Unchecked |  |  |  | Not Executed
TC068 |  |  |  | Log in with valid Email and password | should react on Event action | executed | Sakif4646@gmail.com pass:****** | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Email" field 4.fill with test data 5. click on" Password" feild 6. fill with test data 7.click on "Log In" button |  | Passed
TC069 |  |  | Non functional testing | Log in field with suggested list | should show suggested list or previously login accounts | executed |  | 1. Go to url https://www.upoharbd.com/ 2. Click on "My account" button. 3.click on "Email" field 4.select or chose suggested dropdown list 5. click on" Log in" |  | Passed

## Report
Test Case Report
Project Name - | upoharbd.com
Module Name - | User Management |  |  |  |  | Total No. | Status
Test Case Version | [5 empty] | 44 | PASS
Written By | Sakif Abdullah |  |  |  |  | 21 | FAIL
Executed By | Sakif Abdullah |  |  |  |  | 4 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 44 | 21 | 4 | 0 | 69
Grand Total | 44 | 21 | 4 | 0 | 69
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug report
SL No- | TC007
Issue- | Responsiveness
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3. give invalid input on fields but wont get any immidiate field response
Env- | UAT
Module- | Express Registration
Severity- | P2
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC008
Issue- | Grammatical
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.Observe
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/g1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC010
Issue- | Special character in Name field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p3.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC011
Issue- | Name fields with Number
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot-
Responsible QA- | Sakif Abdullah
SL No- | TC013
Issue- | Name feilds with space input
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "First Name" Fields 4. enter test data 5. click on "Last Name" Field 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p4.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC017
Issue- | Non valid email
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Email" Fields 4. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/p5.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC020
Issue- | country code match with phone number
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/phn6.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC021
Issue- | Phone Number field with space input
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/phn6.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC022
Issue- | specified range in Phone number field(more or less than 11digits)
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Phone No 1" Fields 4. enter test data 5.click on "Phone No 2" Fields 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/phn7.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC030
Issue- | easy guessing password field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Responsible QA- | Sakif Abdullah
SL No- | TC033
Issue- | length requirements (password field)
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Choose Password" Fields 4. enter test data 5.click on "Confirm Password" Fields 6. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/pass1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC035
Issue- | inappropriate or unavailable inputs in address field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC037
Issue- | only Numeric input in address field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Address" Fields 4. enter test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add2.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC040
Issue- | inappropriate or unavailable inputs in Area/town field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC042
Issue- | only Numeric input in Area/Town field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Area/Town" Fields 4. fill test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/add2.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC044
Issue- | only Numeric input in Post/Zip field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Post/zip Code" Fields 4. fill test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/post1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC046
Issue- | CLicking state/District/country dropdown button for other countries(except Bangladesh)
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. Press Bangladesh 5. click on "state/District/country" feild to check dropdown list found 6. click on "Country code" Feild 7. click on any country expect Bangladesh 8. click on " state/District/country" feild which visible no dropdown list 9. fill with test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/country1.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC047
Issue- | Invalid input in state/District/country field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. click on any country expect Bangladesh 5. click on " state/District/country" feild which visible no dropdown list 6. fill with test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/country2.PNG
Responsible QA- | Sakif Abdullah
SL No- | TC048
Issue- | only Numeric input in state/District/country field
Reproducing Step- | 1. Go to url https://www.upoharbd.com/ 2. Click on "Sign up" button. 3.click on "Country code" Fields 4. click on any country expect Bangladesh 5. click on " state/District/country" feild which visible no dropdown list 6. fill with test data
Env- | CI
Module- | Express Registration(Sign up)
Severity- | P1
Screenshot- | https://github.com/Sakif1997/Software-Manual-Testing/blob/main/Bug%20Screenshots/country3.PNG
Responsible QA- | Sakif Abdullah

## Test Metrics
Serial No. | Metrics | Description | Result(%)
1 | percentage of test cases executed | (No. of Test cases Executed/Total no. of Test cases written)*100 | 94.2%
2 | percentage of test cases not executed | (No. of Test cases not Executed/Total no. of Test cases written)*100 | 5.8%
3 | percentage of test cases passed | (No. of Test cases passed/Total no. of Test cases Executed)*100 | 63.76%
4 | percentage of test cases failed | (No. of Test cases failed/Total no. of Test cases Executed)*100 | 30.43%
5 | percentage of test cases blocked | (No. of Test cases blocked/Total no. of Test cases Executed)*100 | 0%
6 | Defect density | (No. of Defects found /Size(No. of Requirements) | N/A
7 | Defect removal efficienct(DRE) | (fixed defects / (fixed defects + Missed defects))*100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of defects found in testing)*100 | N/A
9 | Defect rejection ratio | (No. of Defects rejected/ total no. of defects Raised)*100 | N/A
10 | Defect Age | Fixed date- Reported date | N/A
11 | Customer satisfaction | No. of complaints per Period of time | N/A